## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 9
PROJECT NAME | Room Booking Portal
PROJECT MENTOR (sponsor) | Santhosh
TEAM MEMBERS | Harshit Singh Mehta
Haaris Mohammed Iqbal
Ishaan Shiv Kumar
Mahanth Reddy
Chanakya Manikanta Reddy Arumalla

## Status
PROJECT NUMBER | 9
PROJECT NAME | Room Booking Portal
PROJECT MENTOR (sponsor) | Santhosh
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Harshit | 0.5 | 0.4 | Done |  | 0.1 | 25
Discuss alternate stacks | Preparation | Mahanth | 1 | 1 | Done | Discussed possibility of using a JavaScript stack instead of PHP | 0 | 0
Team Meeting | Coordination | Haaris | 2 | 1.5 | Done | Discussed questions to ask client | 0.5 | 33.3333
Client meeting | Coordination | - | 1.5 | 1 | Done |  | 0.5 | 50
Set roles | Preparation | Harshit | 1 | 1 | Done |  | 0 | 0
Project synopsis writeup | Documentation | Chanakya | 1.5 | 2 | Done |  | -0.5 | 25
Week 2 (January 22 - January 28)
Backend Demo | Preparation | Ishaan, Haaris, Chanakya | 6 | 7 | Done |  | -1 | 14.2857
Frontend Demo | Preparation | Harshit, Mahanth | 5 | 4 | Done |  | 1 | 25
Team Meeting | Coordination | Mahanth, Chanakya | 1 | 1.5 | Done | Discussed and tested prototypes to show to client in meet | -0.5 | 33.3333
Client Meeting | Coordination | - | 1 | 1 | Done | Changed frequency of meeting to biweekly | 0 | 0
Week 3 (January 29 - February 4)
Backend Setup | Development | Ishaan, Mahanth, Chanakya | 2 | 2.5 | Done |  | -0.5 | 20
Week 4 (February 5 - February 11)
Status Tracker | Documentation | Haaris | 1 | 1 | Done |  | 0 | 0
Requirements Document | Testing | Harshit | 1 | 1 | Done |  | 0 | 0
Week 5 (February 12 - February 18)
Status Tracker | Documentation | Mahanth, Chanakya | 1 | 1 | Done |  | 0 | 0
project plan | Documentation | Harshit,Haaris,Ishaan | 2 | 2 | Done |  | 0 | 0
Team Meeting | Coordination | Ishaan, Haaris, Chanakya | 1 | 1 | Done |  | 0 | 0
Week 6 (February 19 - February 25)
Software Requirements specifications | Documentation | Harshit, Mahanth,Chanakya | 2 | 2 | Done |  | 0 | 0
Client meeting | Coordination | Ishaan,Haaris | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | Harshit | 1 | 1 | Done
Week 7 (February 26 - March 4) | [6 empty] | 0.5 | 25
Test plan | Documentation | Mahanth, Ishaan | 2.5 | 2 | Done |  | 0 | 0
Team Meeting | Coordination | Harshit,Haaris | 1 | 1 | Done
Frontend Development started | Preparation | Harshit,Haaris | 3 | 2.5 | Done |  | 0.5 | 16.6667
Backend Develpoment Started | Preparation | Ishaan, Mahanth, Chanakya | 3.5 | 3 | Done |  |  | #REF!
Status Tracker | Documentation | Mahanth | 1 | 1 | Done |  | #REF! | #REF!
Week 9 (March 5 - March 11) | [6 empty] | #REF! | #REF!
Pushed R1 Frontend | Development | Haaris | 6 | 7 | Done |  | -1 | 14.2857
Pushed R1 Backend | Development | Mahanth, Chanakya, Ishaan | 8 | 9 | Done |  | -1 | 11.1111
Week 10 (March 12 - March 19)
Refactored Frontend | Development | Harshit | 2 | 5 | Done |  | -3 | 60
Week 11 (March 20 - March 26)
Team Meeting | Coordination | Mahanth, Chanakya | 1.5 | 1 | Done |  | 0.5 | 50
Week 12 (March 27 - April 2)
Development Paused due to Quizzes and other deadlines
Week 13 (April 3 - April 9)
Team Meeting | Coordination | Ishaan, Haaris | 1 | 1 | Done |  | 0 | 0
Week 14 (April 10 - April 16)
Pushed Notification feature | Development | Haaris | 1 | 3 | Done |  | -2 | 66.6667
Client Meeting | Coordination | Haaris | 1 |  | Planned
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically